## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1812504 |  |  | Week starting: | 11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-23 | 10:00 | 13:00 | 3 | debug the search result page so that the back-end team can use this to present search function | One of the core requirement by the client | Half way done
|  | 13:00 | 14:00 | 1 | Monday routine group meeting | Allocate new tasks, communicate with group members | Next, write the testing plan
|  | 14:30 | 17:00 | 2.5 | Catch up the lectures | learn information about the assignments and project management | Finished all the update lectures
|  | 18:30 | 20:00 | 1.5 | Testing plan structure | Bring the testing to our current development process | Testing plan structure that everyone can contribute
Tuesday | 2022-05-24 | 23:00 | 12:30 | 1.5 | Continue on debugging the search result page which has a persistent bug that I don't know to fix it | A well functioning front-end page that has no visible bugs | Next, try to have deeper knowledge on css
|  | 12:30 | 14:30 | 2 | Learn more JavaScript | There is lots of repeating code in our project, I am thinking get deeper understanding on JavaScript so that maybe could refactoring and modularized it | Have a high level idea how I could operate on this
|  | 14:30 | 17:00 | 2.5 | Testing plan execution part | Integrate the testing part to the development process | First draft of the testing plan
Wednesday | 2022-05-25 | 15:20 | 16:20 | 1 | Wednesday routine group meeting | Update the assignment progress and communicate the necessary project management issues | Group reviewed
|  | 17:00 | 19:00 | 2 | Edit the testing plan according to the group review on the meeting | Integrate the testing part to the development process | Next, execute the testing
Friday | 2022-05-27 | 15:00 | 16:00 | 1 | Friday routine group meeting | Allocate new tasks: write loading page and perform web testing | Loading page can be integrated into our web-application
Saturday | 2022-05-28 | 9:30 | 12:30 | 4 | Write the loading page HTML and CSS code | The current courses rendering takes too long, we need a loading page to enhance the user experience | Finished and commit this page
|  |  | Total | 22