## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1812504 |  |  | Week starting: | 12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-30 | 16:00 | 20:00 | 4 | Debug the visible front-end bugs exist in our web-application | Although we have finished all the major parts of the web-application, we still have some front-end bugs that need to fix to improve the user experience | Fixed a few the fonts, footer, header bus and add keyboard events and pull request
Tuesday | 2022-05-31 | 10:30 | 13:00 | 2.5 | Continue the above tasks | To ensure that we have a unified UI | Next, ready to present these to our client
|  | 13:00 | 14:30 | 1.5 | Group meeting | It was supposed to be a client meeting, but our client didn't show up, so we discussed the internal issues | Next, finish our individual tasks allocated in the meeting
Wednesday | 2022-06-01 | 15:00 | 19:00 | 4 | Watch testing tutorials | Need to learn the basic testing concept and techniques | Next, perform a few testing and record these
|  | 12:00 | 13:00 | 1 | Communicate with group members on how to present our progress to the client | So that our client can know the progress | The meeting with the client went well
Thursday | 2/06/022 | 13:00 | 13:30 | 0.5 | Client meeting | Show our progress and get feedbacks from the client | Positive feedbacks from our client and get more requirements that we might consider doing since it's the end of the project
|  | 13:30 | 15:30 | 1.5 | Group meeting discussed on what requirements we will do and what we won't | Prioritize user stories before the project approaching to end | We promised to deliver two functionalities
Friday | 2022-06-03 | 14:00 | 18:00 | 4 | Perform testing | Test the application | So far the functionalities seem to working fine
Sunday | 2022-05-05 | 15:00 | 17:00 | 2 | Managing requirement documentation and communicate the add functionalities with group members | Keep the documentation up to date | Documentation is up to date on week12
|  |  | Total | 21