## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1812504 |  |  | Week starting: | 9
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-05-02 | 13:00 | 15:00 | 2 | 1. Showcase the progress we have achieved to the client; 2. Get more user stories and requirements from the client; 3. Discuss the new backlogs in our group | To make our application more client-focused | 1. Analyzed and prioritized the new product backlog; 2.Allocated the tasks
|  | 17:45 | 19:00 | 1.75 | Github taskboard management, I labelled all the issues to the correct milstone | Clear development documentation | Created two milestone pools to categorize the development issues of our project.
Tuesday | 2022-05-03 | 13:45 | 16:45 | 3 | Design the prototype of the course relationship page | Visualize the requirement we got it from the client | Finished half of the page design
|  | 17:15 | 20:00 | 2.75 | Design the prototype of the course relationship page | Implementing the design in my head that I didn't finish in the afternoon | Finished the second half of the page design and ready to present my design in tomorrow's meeting
Wednesday | 2022-05-04 | 10:15 | 11:30 | 1.25 | Write the Milestone report | Report our project progress to the supervise | We have a very consistent documentation of the project. Next, headed to our final milestone goal
|  | 15:00 | 17:00 | 2 | Wednesday routine group meeting | Routine group meeting to make decisions and keep our communication on the same page | We decided to use another design. Next, learn Ajax
|  | 18:00 | 19:00 | 1 | Reply to the client | Clarify any vague requirement with the client as soon as possible | Keep a clear communication with the client
Thursday | 2022-05-05 | 17:00 | 18:00 | 1 | Communicate with a group member on how do we implement a user experience | Bring ideas to implementation | Next, try to implement we discussed on discord
Friday | 2022-05-06 | 13:00 | 14:45 | 1.75 | Research the data visualization tool for the course relationship representation | Discover if there is any library we want to use to represent each course object | I listed five npm data visualization tools for the course relationship based on my research, then presented the pros and cons during the meeting
|  | 15:00 | 16:30 | 1.5 | Friday routine group meeting | Routine group meeting to make decisions and keep our communication on the same page | Allocate the upcoming tasks and I will be responsible for the switch button functionality of the home page
Sunday | 2022-05-08 | 10:00 | 12:00 | 2 | Trying to move from Github desktop to git tool, so watched a tutorial | Get to know the fundations of git and manipulate more features of git | I use git command line for the git functions and more
|  | 13:00 | 16:00 | 3 | Research on the static switch button functionality and discussed with group members on its implementation | An advanced functionality that we might develop in our application | Next, update my progress on Monday's meeting
|  |  | Total | 23