## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 10
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-16 | 14:00 | 15:00 | 1 | Sprint planning meeting to determine the user stories to be finished in this sprint, and assign task for each member | Agile development approach can improve our efficiency | I will need to inject data to EJS file. The current file should be refactored.
Tuesday | 2022-05-17 | 11:00 | 13:00 | 2 | Refactor the course overview page so that I can inject dynamic data into it | To finish the course overview page, and milestone 2 | Now I can inject some data on course overview page. But I still need some other data (the 'belongs_to' data). That is the job of Yuhao. I will wait until he can finish his part and send the data to me.
|  | 18:00 | 19:30 | 1.5 | Create the timesheet of week 9 | To do project management | Finished
Wednesday | 2022-05-18 | 15:00 | 16:00 | 1 | Group meeting to report individual progress and determine the structure of our testing plan | Agile development approach can improve our efficiency | We will go to make a testing for assignment
|  | 18:00 | 20:00 | 2 | Rearch on different types of testing approch and determine which one is suitable for our project. Write my part of testing plan (testing strategy) | Assignment. A testing plan can give use direction of how we are going to test the application | Finished
|  | 21:00 | 21:30 | 0.5 | Set up a folder and create css, html files inside. This folder is for frontend members to create searching result page. | To finish the searching result page, and milestone 2 | Finished. Now I will wait unitl the frontend member to create a prototype of searching result page. Then I can inject dynamic data into the page.
Thursday | 2022-05-19 | 9:00 | 11:00 | 2 | To get the 'belongs_to' data, we need asynchrous query function. I undertake this task and try to fix it with async pack | To get the data that the client require and render them on webpage which is an important part of milestone 2 | Data can be access by async package using async.forEachof() function. But the return data is blank because the database query function inside is still asynchronous. I need to find a way to implement synchronous database query function
|  | 11:00 | 12:00 | 1 | Do some research to find a synchronous database query. | To get the data that the client require and render them on webpage which is an important part of milestone 2 | Finished. I can use mysql2 package instead of mysql to do synchronous database query with await statement. Now we can get 'belongs_to' data for each course.
Friday | 2022-05-20 | 15:00 | 16:00 | 1 | Group meeting to report individual progress | Agile development approach can improve our efficiency, and have a review on testing plan | I will make a table to show the relationship between client requirements and acceptance criteria
|  | 18:00 | 19:00 | 1 | Make a table to show the relationship between client requirements and acceptance criteria | Assignment. A testing plan can give use direction of how we are going to test the application | Finished. Next I will inject the 'belongs_to' data into course overview page
Saturday | 2022-05-21 | 11:00 | 12:30 | 1.5 | Inject the 'belongs_to' data into course overview page | To render the data that the client require and render them on webpage which is an important part of milestone 2 | Finished. I will go to learn fetch api which I think should be used for degree structure page
Sunday | 2022-05-22 | 18:00 | 19:00 | 1 | Learning fetch api and write a simple example of getting data from the server | To prepare for creating degree structure page, which is an important part of milestone 2 | Finished. Next meeting I will show the team about how fetch api works
|  |  | Total | 15.5 | I expect to spend more time in development on the next two weeks