## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 11
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2023-05-23 | 22:00 | 22:30 | 0.5 | Write timesheet for week 10. Also review what I have done for the last week. | Project management | Next I will prepare to show the fetch api for the team
|  | 10:30 | 10:45 | 0.25 | Write a diagram to show how fetch api works | This is to share knowledge and in case some members will use this tool in the future | Finished. Yingyu produced some HTML and CSS code for course relationship page. I will take a review on it.
|  | 12:00 | 12:20 | 0.3 | Review the HTML, CSS code of course relationship page. | To finish the course relationship page, and milestone 2 | Well, there barely has gap between course cards. I will tell Yingyu to modify it.
|  | 15:00 | 15:30 | 0.5 | Group meeting to Group meeting to report individual progress, and task assignment | Agile development approach can improve our efficiency. Each member can know their next step. | My task is to inject dynamic data to the course relationship page and degree structure page.
|  | 15:30 | 15:45 | 0.15 | Document the meeting minutes | Project management. Meeting minutes are reminder for all the team member | Finished. Next, I will inject dynamic data to the degree structure page.
Tuesday | 2023-05-24 | 11:00 | 15:00 | 4 | Inject dynamic data into degree structure page | To finish the degree structure page, and milestone 2 | I found some bugs in the data, I will report them to Yuhao since he is responsible for the data.
|  | 19:00 | 21:30 | 2.5 | Inject dynamic data into course relationship page | To finish the course relationship page, and milestone 2 | Almost finished. Got some minor problems, will fix them.
Wednesday | 2023-05-25 | 15:00 | 16:00 | 0.5 | Group meeting to report individual progress and and task assignment | Agile development approach can improve our efficiency | I will keep working on the course relationship page, also waiting for Yuhao fixing the data problem.
Friday | 2023-05-27 | 15:00 | 16:00 | 1 | Group meeting to report individual progress and and task assignment | Agile development approach can improve our efficiency, and have a review on testing plan | I will keep working on the course relationship page, also waiting for Yuhao fixing the data problem.
|  | 18:00 | 18:30 | 0.5 | Fix some minor problem in the course relationship page | To finish the course relationship page, and milestone 2 | Good. Our course relationship page, one of the projected outputs of milestone 2, is finished! Data problem is fixed by Yuhao, so I will keep making the degree structure page.
|  | 18:30 | 19:00 | 0.5 | Inject the new dynamic data into the degree structure page. | To finish the degree structure page, and milestone 2 | Finished. Next I will integrate a loading page into our website since sometimes the response time is long.
|  | 19:00 | 20:30 | 1.5 | searching how to integrate the loading page into our website and create the loading page based on exsiting HTML, CSS code by Ying | To improve the user experience. | Finished. Searching result page is prepared, I will integrate it into our website.
Saturday | 2023-05-28 | 11:00 | 11:45 | 0.75 | Integrate the searching result page into our website. | To finish the searching result page, and milestone 2 | Now our searching result page, one of the projected outputs of milestone 2, is finished! I am waiting for Yingyu to finish the layout of edit/add course section.
Sunday | 2023-05-29 | 18:00 | 19:00 | 0.8 | Have a review on the add/edit course section. Also consider how to integrate them into the degree structure page. | To finish the edit/add course functionality, and milestone 2 | I found some problem in the code, I will report them to Yingyu.
|  |  | Total | 13.75
Our development part is approching to the end. I expect to spend more time on implementing the edit/add course functionality