## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-09 | 11:00 | 13:00 | 2 | Upload milestone 1 project file and fix the verson error by git | To deliver our milestone project | Finish
|  | 15:00 | 16:00 | 1 | Group meeting to discuss the task assignment | Agile development approach can improve our efficiency | I am going to making lecture note to have a better learning on how to write testing plan
|  | 19:00 | 21:00 | 2 | Carefully watch the lecture about testing plan, writing notes that may be helpful for our discussion on how to structure our testing plan | To deliver a high-quality testing plan | Finished. Next I am going to manage github file, and learn how to modify the selection list to pass the selected value to back end
|  | 21:00 | 21:30 | 0.5 | Management github files and add comment on files to indicate the milestone 1 files | To do project management | Finished. Next I am going to learn how to to modify the selection list
Tuesday | 2022-05-10 | 10:00 | 12:00 | 2 | Learn how to convert the current selected list into a "input" element of "select" type | To implement the searching functionality | "Input" element of a "select" type can not be modified. Maybe I should consider using DOM operation and not changing the current selection list that front end was provided.
|  | 12:00 | 14:00 | 2 | Since one front end member could not implement a static page switching, I should go to search something about Ajax to see whether I can implement it | To implement a static page switching | If I choose to use Ajax, the ejs file should be converted to html. That will be a time-consuming refactor and not making much difference. So I decided to set aside this issue. I will next try to implement the DOM operation and pass selected value to back end
|  | 14:00 | 5:00 | 3 | implement the DOM operation and pass selected value to back end | To integrate the front end and back end | I use query selector and successfully pass the selected value to the back end. Next I will go to deal with the searching bar
|  | 18:00 | 21:30 | 2.5 | One member transferred the static searching bar into a input area where user can type in text for making data query. But this member failed to maintain the design of the searching bar. So I should find a better way to make the searching bar being able to accept user input while maintaining it design. | To implement the searching functionality | I finished my task. Next I will integrate the searching bar with back end
Wednesday | 2022-05-11 | 10:00 | 12:30 | 2.5 | Implement searching function: when user enter some text into the searching bar, the back end should be able to receive the text, do searching according the text, and return the result. My task is to make a API to accept this text, and make a route for user to access and see the searching result | To implement the searching functionality | I finish my task.
|  | 15:00 | 17:00 | 3 | Group meeting to report individual progress and discuss the milestone 2 plan | Agile development approach can improve our efficiency | I will draft the milestone 2 plan since I have a better understanding of this project.
|  | 19:00 | 20:30 | 1.5 | Draft the Milestone 2 plan | To finish the assignment, also give team members a clear direction for the following weeks | Finished
Thursday | 2022-05-12 | 10:00 | 15:00 | 5 | Convert the degree structure page to a ejs file. This require me to refactor the html page and the path of injecting css files | To create a dynamic degree structure page | Finished. Now the page can dynamically change its content according to the data it receives
Friday | 2022-05-13 | 15:00 | 17:00 | 2 | Group meeting to report individual task progress and review the milestone 2 plan | Agile development approach can improve our efficiency. And to do the assignment | I will next go to deal with the course overview page
|  | 19:00 | 20:30 | 1.5 | Convert the course overview page to a ejs file. This require me to refactor the html page and the path of injecting css files | To create a dynamic course overview page | Not Finished. The page somehow cannot receive data.
Satuday | 2022-05-14 | 10:00 | 12:00 | 2 | Document the group meeting agenda, meeting minutes for this week | To do project management | Finished. There is a scroll down bug in the course overview page that cannot be fixed by other members, so I will take it and see how to fix it
|  | 13:00 | 14:30 | 1.5 | Fix the problem in the course overview page: cannot scroll down when there are multiple lines of course cards | To create a dynamic course overview page | Problem fixed.
|  | 19:00 | 22:30 | 3.5 | Convert the course overview page to a ejs file - and to make the page to be able to receive the data. This require me to refactor the html page and the path of injecting css files | To create a dynamic course overview page | Half Finished. ow the page can receive some data. But data is not prepared, I will wait until other member is able to prepare necessary data.
|  |  | Total | 37.5