## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-30 | 10:00 | 10:55 | 1 | Write week11 timesheet to record all the tasks I did last week | To summarize personal progress and do project management | Finished
|  | 11:00 | 15:00 | 3 | Add add-icon and edit-icon and create the skeleton of adding courses, edit courses in degree structure page. | To implement the add/edit course functionality and realize milestone 2 | Now the add/edit course buttons are added into the degree structure page. I will tell Yingyu to repalce the pop up window with formatted forms
Tuesday | 2022-05-31 | 13:00 | 14:00 | 1 | Group meeting to do task assignment and summarize the current progress and next steps | To give members a clear direction for the next weeks and realize milestone 2 | Next I will continue to build the structure of add/edit course buttons
|  | 15:00 | 17:00 | 2 | Set up a simple demo of using fetch api to pass data from frontend to backend | To prepare for transferring form data to backend server. This is also for implementing add/edit course functionality | Now I can send JSON data to backend by using fetch api with POST method
Friday | 2022-06-03 | 15:00 | 15:30 | 0.5 | Group meeting to do task assignment and summarize the current progress and next steps | To give members a clear direction for the next weeks and realize milestone 2 | Github branches are in a mess, I will revert the version and find out our timesheets and upload them to a new brnach
|  | 17:00 | 18:00 | 1 | revert the project and find out our timesheets and meeting minutes, agendas and upload them to a new brnach | To do project management | All files were uploaded to a new branch
|  | 19:00 | 19:15 | 0.25 | Debug the degree structure page of "bachelor of computer science advanced" | Bug fix | Now the courses can shown on this page
Sunday | 2022-06-05 | 18:00 | 19:30 | 1.5 | Document the cilent meeting minutes and group meeting minutes | To do project management | Finished
|  |  | Total | 10.25
Our client proposed new requirements. I expect to spend more time on implementing the new requirements