## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 13
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-06-06 | 15:00 | 16:00 | 1 | Group meeting to do task assignment and summarize the current progress and next steps | To give members a clear direction for the next weeks and realize milestone 2 | Next I will deal with the new requirements proposed by our client at the last client meeting
|  | 17:00 | 19:30 | 2.5 | Create the "add new course" button and the skeleton of "add new course" form | To realize the new client requirement | Finished. I will tell Yingyu to replace the pop up window with a formatted form
|  | 19:30 | 19:45 | 0.15 | Hide degree structure btn when loading-delete extra add course in degree structure page | To improve the user experience | Finished
|  | 20:00 | 23:00 | 3 | Collect the "add course" and "edit course" form data by using JS DOM operation | To implement the add/edit course functionality and realize milestone 2 | Finished. Next is to transfer the collected "add course" form data to the backend
Tuesday | 2022-06-07 | 10:00 | 12:00 | 2 | Transfer the collected "add course" form data to the backend | To implement the add/edit course functionality and realize milestone 2 | Finished. Next is to transfer the collected "edit course" form data to the backend
|  | 13:00 | 15:00 | 2 | Transfer the collected "edit course" form data to the backend | To implement the add/edit course functionality and realize milestone 2 | Finished. The "edit course" function is implemented.
|  | 17:00 | 18:20 | 1.3 | Create the "add new degree" button and the skeleton of "add new degree" form | To realize the new client requirement | Finished. I will tell Yingyu to replace the pop up window with a formatted form
Wednesday | 2022-06-08 | 15:00 | 16:00 | 1 | Group meeting to do task assignment and summarize the current progress and next steps | To give members a clear direction for the next weeks and realize milestone 2 | Next I will keep deal with the new requirements proposed by our client at the last client meeting
|  | 18:00 | 18:30 | 0.5 | Collect the "add new course" form data by using JS DOM operation and Transfer the collected form data to the backend | To realize the new client requirement | Finished. The "add new course" function is implemented.
|  | 18:30 | 19:45 | 1.75 | Integrate a searching functionality into "add course" form and render the searching result | To implement the add/edit course functionality and realize milestone 2 | Finished. The "add course" function is fully implemented.
Thursday | 2022-06-09 | 10:00 | 11:55 | 1.9 | Improve the "add new degree" form, collect the "add new course" form data by using JS DOM operation and transfer the collected form data to the backend | To realize the new client requirement | Finished. The "add new degree" function is implemented.
Friday | 2022-06-10 | 15:00 | 16:00 | 1 | Group meeting to do task assignment and summarize the current progress and next steps | To give members a clear direction for the next weeks and realize milestone 2 | Milestone 2 is finished. Next I will keep working on the new client requirements
|  | 18:00 | 20:00 | 2 | Implement "delete degree" and "delete stream" functionalities | To realize the new client requirement | Finished. Client wants to add an existing course to multiple degree. My task is to show them what degrees and streams can they add a course in. To do so, I will first create a new table in database which contains all the degrees and streams that are currently in our website
Satuday | 2022-06-11 | 10:00 | 12:30 | 2.5 | Create a "degree_streams" table in database to store all the degrees and their streams that are currently in our website | To realize the new client requirement | Finished. Next is to show the table to client
|  | 12:30 | 13:00 | 0.5 | Render all the degrees and their streams in "add course" form | To realize the new client requirement | Finished. Now the client can add an existing course to multiple degree
|  | 13:00 | 15:00 | 2 | Adjust the edit button and integrate 404 page | To make our website more user friendly | Finished. Now if user access a webpage that does not exist, the server will return a 404 page
|  | 19:00 | 19:30 | 0.5 | Draft a new software architecture since we have added lots of new components in our web application | Prepare for the poster and final report | Finished
|  |  | Total | 25.6
This is the end of our web development