## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 8
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-02 | 1:00 | 1:30 | 0.5 | Client meeting to show project | Agile development process | Finish presentation and get requirement update
|  | 13:30 | 14:00 | 0.5 | Sprint 5 planning meeting | Agile development process | I will do some file mangement in this sprint
Tuesday | 2022-05-03 | 11:00 | 15:00 | 4 | Learn more about api, focusing on how to do post and delete route | To learn essential programming skills | Keep learning
Wednesday | 2022-05-04 | 11:00 | 11:40 | 2.6 | Manage files in github, writing essential project description | project management | Finished
|  | 3:00 | 5:00 |  | Scrum meeting to reflect on current progress and decide next step | Agile development process | We should do the milestone report
Sunday | 2022-05-08 | 19:00 | 8:00 | 1 | Reword milestone 1 report | To fulfill milestone 1 report | Finished
|  |  | Total | 8.6
This week I spent less time on MCI project. The reason is that, as a back end member, I have finished the basic structure of the website and been waiting for front end members to finish their website design and coding. Only after they finish their works, can I start adding routers and logic to back end and combine the front end and back end together. I expect to spend more time on development next week once they can deliver the basic html, css, and js code. Or I will engage in front end development.