## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1812504 |  |  | Week starting: | Mid-term break2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Tuesday | 19/04/2022 | 9:30 | 10:00 | 0.5 | Send out this week's meeting invitation since I'm the current scrum master | Team members can arrange the meeting time more flexible | Next, establish these effective process management
|  | 13:00 | 14:00 | 1 | Prepare the Sprint Planning Meeting | Have a high effective meeting | The meeting was very effective
|  | 14:00 | 16:30 | 2.5 | Host the Sprint Planning Meeting | 1.Current Project Showcase 2. Sprint backlog update 3. Reviewed team availability 4. Task assignment | Clear tasks and sprint goal
|  | 4:30 | 5:30 | 1 | Generate meeting minutes and manage github taskboard | Have an effective development process | Next, follow the assigned tasks
Wednesday | 20/04/2022 | 9:00 | 11:00 | 3 | Determine using EJS or React.js | Closed the related github issue | Generate the documentation on how the decision was made
|  | 12:00 | 16:00 | 4 | Looking for better search bar desgin on CodePen | Have a better understanding on how to upgrade the search bar | Next, try to run the code on the project
|  | 18:00 | 21:00 | 3 | Research how to parse JSON file to python local server | essential document processing | Proved the difficulties of these method
Thursday | 21/04/2022 | 16:00 | 17:00 | 1 | Prepare the Sprint Task Update meeting | Have a high effective meeting | Tasks are align with the sprint goal
|  | 17:00 | 18:00 | 1 | Host the Sprint Task Update Meeting | 1. Front-end design showcase 2. Research the front-end tools | Next, try to use more automatic tools
|  | 18:00 | 19:00 | 1 | Generate meeting minutes and manage github taskboard | Have an effective development process | Closed issues
Friday | 22/04/2022 | 14:00 | 15:00 | 1 | Prepare the 'Sprint Demo Friday' meeting | Have a high effective meeting | Tasks are align with the sprint goal
|  | 15:00 | 16:00 | 1 | Host the 'Sprint Demo Friday' meeting | 1. Front-end design showcase 2. Research the front-end tools | Next, try to use more automatic tools
|  | 4:00 | 5:00 | 1 | Generate meeting minutes | Have an effective development process | Closed issues
Saturday
|  |  | Total | 21