## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1812504 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 27/04/2022 | 8:00 | 9:00 | 1 | Plan this week's meeting agenda and sending out the invitations | Arrange effective meetings to help internal communication | Next, host the iteration review, task update and retrospective meetings
|  | 12:30 | 1:00 | 0.5 | Prepare the 'Iteration Review' Meeting | Have good communication among group members | We reviewed if our development process align with the sprint goal as this is the half of the sprint
|  | 13:00 | 14:30 | 2.5 | Host the Iteration Review Meeting | Set checkpoint to exam the development process | Archived more than 11 github issues
|  | 14:30 | 15:00 | 0.5 | Generate meeting minutes and manage github taskboard | Have an effective development process | Next, follow the assigned tasks
Tuesday | 28/04/2022 | 9:30 | 11:30 | 2 | Try to write the degree page's html and css code | Fast development | Next, looking for more online examples
Wednesday | 29/04/2022 | 14:00 | 14:30 | 0.5 | Prepare 'Milestone 1 Report & Task Update' Meeting | Clear agenda and goals | Next, focusing on executing them
|  | 15:00 | 16:30 | 1.5 | Host 'Milestone 1 Report & Task Update' Meeting | Alloacting tasks fairly | Clear task alloacting
|  | 16:30 | 17:30 | 1 | Generate meeting minutes | Provide essential documentation | Next, tracking the tasks
Thursday | 30/04/2022 | 16:00 | 18:00 | 2 | Write my part of the Milestone 1 Report | Have a better understanding on our project progress | first draft
|  | 20:00 | 10:00 | 2 | Watch tutorials on python local server | Have a better understanding on the project | Next, try to deploy on my own laptop
Friday | 31/04/2022 | 7:00 | 8:30 | 1 | edit my part of the Milestone 1 report | Improving my report writing skill | second version
|  | 12:30 | 1:00 | 0.5 | Prepare 'Sprint retrospective' Meeting | Analyze what went well and what didn't work in the project process | So we will have revised actions
|  | 13:00 | 15:00 | 2 | Host 'Sprint retrospective' Meeting | Routine communication and task update | Next, prepare new sprint
|  | 15:00 | 16:00 | 1 | Generate meeting minutes | Provide essential documentation | Uploaded to group file
Saturday | 2022-01-05 | 9:30 | 12:30 | 3 | Watch lectures | Learn the essential concepts in project mangement and catch up the assignment | Next, prepare new sprint
|  |  | Total | 21