## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | week 9 (09/05/2022-15/05/2022)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-09 | 5:30 | 6:00 | 0.5 | Update my timesheet to Github | Project management | Next step is to plan my work in this week.
|  | 14:30 | 15:00 | 0.5 | Before the group scrum meeting, I should plan my to do tasks in this week and set the deadline of them, and put them on GitHub, then my teammates will know my schedule of design. | Self management | They can plan their work according to my output.
|  | 15:00 | 16:00 | 1 | Group meeting to update everyone's work. | Project management | I was assigned to update the design documents and refill some README files.
|  | 17:30 | 19:45 | 2.25 | Design the design-system file. | Project management | Next action is to update the files on GitHub.
|  | 20:30 | 23:00 | 2.5 | Supplement README files and update wireframe works and prototype design and design system to GitHub. | Project management | Tomorrow need to deliver the degree structure page.
Tuesday | 2022-05-10 | 13:30 | 15:00 | 1.5 | Debug the homepage-Degree | Project development | Next is going to debug the homepage-course section
|  | 15:15 | 17:45 | 2.5 | Debug the homepage-Course | Project development | Already update to my own branch, and inform other teammate to optimize other functions.
|  | 19:15 | 23:15 | 4 | Design the course relationship page | Project development | Waiting for the feedback from teammates, I will do further refine after the scrum meeting.
Wednesday | 2022-05-11 | 23:00 | 15:00 | 4 | Refine homepage, in these part, I start learning user Bootstrap to implement basic components in an easier way. | Project development | Update the toogle button and the navigation bar.
|  | 15:00 | 17:00 | 2 | Group meeting to update everyone's work and negotiate what need to redo and plan for the milestone 2 plan. | Project management / Scrum meeting | The search part of the homepage needs debug to get the input from the user.
Thursday | 2022-05-12 | 16:00 | 22:00 | 6 | Revise the course relationship page according to the suggestions from teammates. | Project development | At first we were about to use a mindmap to display the relationship of courses but it has some difficult in different kinds of degree. So finally we decided to still use the column and cards to display the relationship page.
Friday | 2022-05-13 | 11:30 | 15:00 | 3.5 | Revise the course relationship page into responsive page. | Project development | It is really important for the page that can be responsive for different tool such as phone and tablet and laptop.
|  | 15:00 | 17:00 | 2 | Group meeting to update progress and review the milestone2 plan | Project management / Scrum meeting | The relationship page is basically finished, after that I will design the search result page which will return all the results of searching function.
|  | 19:15 | 20:15 | 1 | Go through the milestone 2 and revise a little bit. | Project management | According to Ruwen's base on milestone 2, we did a little revise.
Sunday | 2022-05-15 | 21:00 | 22:00 | 1 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. | Self management | Finished the timesheet of this week. Next week is to finish the search result page.
|  |  | Total | 34.25