## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | week 10 (16/05/2022-22/05/2022)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-16 | 14:00 | 15:00 | 1 | Group meeting to update everyone's work and clarify the new sprint's tasks and assign the tasks to each member. | Project management | I am going to finish the search result page and do small adjustment to the refactored EJS file.
|  | 17:30 | 22:00 | 4.5 | Learn The Complete 2022 Web Development Bootcamp EJS part | Learning basic skill to support my development | Learnt aboout what is EJS and how to modify the outlook of webpage through EJS file.
Tuesday | 2022-05-17 | 23:30 | 15:00 | 3.5 | Design the search result page. | Project development | Next is going to implement the page from the HTML and CSS code.
|  | 19:00 | 23:30 | 4.5 | Implement the code of the search result page. | Project development | Push the code to my branch for back-end team to refactor.
Wednesday | 2022-05-18 | 15:00 | 16:00 | 1 | Group meeting to update everyone' work and prepare for the testing plan assignment. | Project management | We are going to learn more about testing plan and make some testing.
|  | 19:00 | 23:00 | 4 | Learn the basic concept for the testing. | Learning basic skill to support my development | Did some research on different types of testing approach and choose the one that suitable for front-end.
Thursday | 2022-05-19 | 16:00 | 22:00 | 6 | Refine the EJS file of the homepage, debug the format such as footer and height of the cards. | Project development | It will have new bugs when input the real data to the front end template, so this time needs to debug and do some adjustment.
Friday | 2022-05-20 | 11:00 | 13:00 | 2 | Writing my part of the testing plan. | Project management / Assignment | I finished introduction part.
|  | 15:00 | 16:00 | 1 | Group meeting to update everyone' work and review the testing plan in group. | Project management | Next step is to keep refine the bugs on the pages that already refactored.
|  | 22:00 | 23:00 | 1 | Final revise for the testing plan. | Project management / Assignment | Edit the grammar error and do some supplement to the testing plan.
Sunday | 2022-05-21 | 21:00 | 22:00 | 1 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. | Self management | Finished the timesheet of this week. Next week is to refine the previous pages.
|  |  | Total | 29.5