## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | week 11 (23/05/2022-29/05/2022)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-23 | 15:00 | 15:30 | 0.5 | Group meeting to update everyone's work and clarify the new sprint's tasks and assign the tasks to each member. | Project management | There are still some bugs that needs to fix after injecting data into template. So I need to fix them.
|  | 18:30 | 12:00 | 5.5 | Fixing the bugs in the already done pages. | Project development | Next step is to implement the popup modal like editing, adding,deleting and so on.
Tuesday | 2022-05-24 | 13:30 | 17:00 | 3.5 | Learn how to made popup modal on a page. | Learning basic skill to support my development | Next step is to finish the design and share to my teammates and ask for feedback.
|  | 20:00 | 23:30 | 3.5 | Design the UI of add,edit,delete modal. | Project development | Push the code to my branch for back-end team to refactor.
Wednesday | 2022-05-25 | 15:00 | 16:00 | 1 | Group meeting to update everyone' work and prepare for the testing plan assignment. | Project management | Design passed, next step is to implement into codes.
|  | 19:00 | 23:00 | 4 | Implement the degree add/edit/delete modal. | Project development | This time the code will cooperate with the JavaScript and jQuery as well. So I need to spend sometime to learn more about JS and jQuery.
Thursday | 2022-05-26 | 16:00 | 19:00 | 3 | Learn more about the interact in JS with jQuery and DOM | Learning basic skill to support my development | It will have new bugs when input the real data to the front end template, so this time needs to debug and do some adjustment.
Friday | 2022-05-27 | 15:00 | 16:00 | 1 | Group meeting to update everyone' work and review the testing plan in group. | Project management | The implement of modal is success,but I was using new HTML and CSS, I need to implement that into the existed EJS code.
|  | 19:00 | 1:00 | 6 | Implement the degree add/edit/delete modal. | Project development | Add the code to EJS and debug.
Sunday | 2022-05-29 | 21:00 | 22:00 | 1 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. | Self management | Finished the timesheet of this week. Next week is to finish the add /edit/delete course modal.
|  |  | Total | 29