## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | week 13 (06/06/2022-12/06/2022)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-06-06 | 13:00 | 14:00 | 1 | Group meeting to update everyone's work | Project management | Got the popup template for course adding and editing. Next step is to implement code into it.
|  | 20:00 | 23:30 | 3.5 | Got feedback from Ruwen that popup need to be reformat. | Project development | Re-implement the popup modal and then push to my branch for her to inject the data.
Wednesday | 2022-06-08 | 11:00 | 15:00 | 4 | Change the form of "add new degree button" and debug the add degree modal. | Project development | Re-implement the add degree modal and then push back to my branch.
|  | 15:00 | 16:00 | 1 | Group meeting to update everyone's work | Project management | I found when the user doesn't have valid input will return a blank page with simple one sentence. So I decided to design a 404 page.
|  | 13:00 | 14:00 | 1 | Made a 404 page when doesn't have valid input in search bar. | Project development | Developing is almost finish, it is time to prepare for the poster and demo presentation.
Friday | 2022-06-10 | 15:00 | 16:00 | 1 | Group meeting to update everyone's work | Project management | The due of the codes submission is on 12th, so we have two more days to sort out the codes and tidy them.
Saturday | 2022-06-11 | 16:00 | 22:00 | 6 | Summarize the content for the poster and make the draft of the presentation post,and write the script. | Project management / Assignment | Design the poster and practice for the presentation.
Sunday | 2022-06-12 | 21:00 | 22:30 | 1.5 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. | Self management | Finished the timesheet of this week. Next week is to finish the add /edit/delete course modal.
|  |  | Total | 19