## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-03-07 | 19:00 | 21:00 | 2 | Research on where we can get the details of courses. Research on how to get courses details from uni. Do group documentation | Data are all from the uni website. I should find a way to get these data. | Check about Python data mining
|  | 13:00 | 13:45 | 0.75 | Client meeting and Sprint 1 meeting | It is a meeting to assign tasks to each team member | Each team member should learn how to grab data
Tuesday | 2022-03-08 | 20:45 | 21:15 | 0.5 | Research on how Python can be used to do data mining | I knew that Python could be a tool to grab data. | I can simply use the "request" library. But team member Yuhao said there is a more convenient tool called webscraper so Python was shelved
Wednesday | 2022-03-09 | 14:30 | 15:30 | 1 | Sprint 1 meeting | It is a meeting to assign tasks to each team member | I will learn MySQL to know how to draw a diagram of database prototype
|  | 16:00 | 18:30 | 2.5 | Learn about the basic command in MySQL | Data from the uni system should be store in database. So it is improtant to design our database | I will try to draft the design of our database
|  | 20:00 | 21:00 | 1 | Writing lecture notes | I should conclude the points of pitch presentation and business case | I made some conclusion so that I can refer to when doing the pitch slide.
|  | 21:00 | 21:30 | 0.5 | Draft the database diagram | Data from the uni system should be store in database. So it is improtant to design our database | Lucichart was a new tool for me and I think it was hard to manipulate so I decided to use excel tomorrow instead.
Thursday | 2022-03-10 | 10:00 | 11:30 | 1.5 | Draft the database diagram | Data from the uni system should be store in database. So it is improtant to design our database | I used excel to draft our database diagram. I should discuss with Yuhao who is with me responsible for building database
|  | 14:10 | 14:40 | 0.5 | Check with Yuhao about my database diagram and the courses data he grabbed from the uni system | Course data is the main part of our project | Yuhao agree with my database diagram. Grabbed data were in a mess. I said if he could not find out a more effective way to organize data, we should try to use the "Request" library in Python.
|  | 17:00 | 17:30 | 0.5 | Draft our requriement documentation and inform my group memebrs | A clear requirement documentation can give us clear direction | Finish draft. We should discuss it at the next group meeting (tomorrow)
Friday | 2022-03-11 | 0:00 | 15:00 | 3 | Sprint 1 meeting | This is an essential meeting as we should decide our project plan for each week until the first milestone | We had a detailed plan for each week. And we should futher clarify requirements with our client. I will learn JavaScript as the next step.
|  | 21:00 | 22:00 | 1 | Write Gantt Chart and other documentations | For project management | I finished my part of the Gantt Chart.
Saturday | 2022-03-12 | 19:00 | 21:00 | 2 | Construct template for meeting minutes and meeting genda. Write documents which are related to project management. | Well-organized documentation helps to improve efficiency | I listed user stories that we are going to implement for sprint 2. I revise the template of meeting minute and meeting agenda.
Sunday | 2022-03-13 | 11:00 | 11:30 | 0.5 | Learn about JavaScript | To develop essential programming skill | I will continue to learn basic syntax
|  | 11:30 | 0:00 | 0.5 | Arrange our scrum meeting and prepare related resource | To make sure the meeting will go smoothly | Finish Preparation
|  | 18:00 | 20:00 | 2 | Learn about JavaScript | To develop essential programming skill | Finish learing string/number conversion. I will continue to learn basic syntax
|  | 22:45 | 23:15 | 0.5 | Confirm documents required by Project Plan. | To satisfy course requirements | It will be discussed in Monday's meeting
|  |  | Total | 20.25