## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 5
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-03-28 | 10:00 | 10:30 | 0.5 | Learning the basic of view engine ejs. | To learn essential programming skill | I know that ejs is a sort of dynamic html, which is useful for displaying data, which is sent back by server, onto browser
|  | 11:00 | 12:00 | 1 | Scrum meeting to discuss pitch slide, giving suggestion to each other | To deliver a pitch presentation | All team members should refine the slide again and then send the slide to the course director for feedback
|  | 13:00 | 16:30 | 3.5 | Refine my part of pitch slide and speech script | To deliver a pitch presentation | I finished my part of pitch slide and speech script
Tuesday | 2022-03-29 | 18:00 | 21:00 | 3 | We received the feedback from the course director. So, again, refine my part of pitch slide and speech script according to the feedback. And, rehearse my part of presentation before next scrum meeting | To deliver a pitch presentation | I finished my part of pitch slide and speech script. And I should rehearse more on tomorrow.
Wednesday | 2022-03-30 | 12:00 | 14:00 | 2 | Rehearse my part of presentation before next scrum meeting | To deliver a pitch presentation | I have prepared to do presentation in scrum meeting.
|  | 15:00 | 17:45 | 2.75 | Scrum meeting to discuss pitch slide, giving suggestion to each other based on check-list, marking criteria and feedback provided by the course director | To deliver a pitch presentation | I should refine my pitch slide as a member suggested that role information is duplicated in the slide 'meet the team'. And I should consider a more concise and accurate description on 'grow market size'
|  | 18:30 | 19:00 | 0.5 | Refine my pitch slide again.Rehearse my part of presentation | To deliver a pitch presentation | I think this is the final version of my part of pitch slide and speech script.
|  | 19:00 | 7:30 | 0.15 | Record all the activities today and write into timesheet. And make plan for tomorrow. | Project management | My plan for tomorrow is to finish recording of my pitch presentation.
Thursday | 2022-03-31 | 18:00 | 20:30 | 2.5 | Other members' part of pitch slide still need revision. So we should have a meeting to refine the pitch slide page by page. Also I comfirm some details with members about the format of pitch slide | To deliver a pitch presentation | I will start recording my part of pitch presentation tomorrow.
Friday | 2022-04-01 | 14:00 | 15:00 | 1 | Record my part of presentation | To deliver a pitch presentation | Ying Liao and I are responsible for project plan, so I will start to draft the project plan tomorrow
Satuday | 2022-04-02 | 13:30 | 14:30 | 1 | Get to know the marking criteria of project plan, and do work division with Ying Liao | To make a draft plan | I will be responsible for milestone plan.
|  | 14:30 | 16:30 | 2 | Write a gantt chart. Specify which acitivities are required to achieve milestone 1. Confirm it with team members | To make a draft plan | Waiting for discussion with team members about some details, so I will do the milestone plan next.
|  | 19:00 | 20:00 | 1 | Writing a milestone plan based on the exisiting information in gantt chart | To make a draft plan | Tomorrow will continue to specify projected output for the last 3 activities.
Sunday | 2022-04-03 | 18:00 | 21:30 | 3.5 | I got some feedback from my teammate about the milestione plan, so I should modify the milestone 1 plan | To make a draft plan | I have several places of the milestone plan remain uncertain. We will discuss it on tomorrow's meeting.
|  |  | Total | 24.4