## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | Mid-break week 2 (18/04/2022 - 24/04/2022)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-04-18 | 13:00 | 15:30 | 2.5 | Learn The Complete 2022 Web Development Bootcamp the document model(DOM) part | Learning basic skill to support my development | Learnt about DOM
Tuesday | 2022-04-19 | 14:00 | 16:30 | 2.5 | Scrum group meeting, we reviewed the previous sprint and assigned tasks to do for each member. | Project management / Scrum meeting | Need to decided the design of all pages.
|  | 18:30 | 20:30 | 2 | Learn how to use github | Project development | Now I know how to push the codes and files to my own branch, and how to pull requests to the master branch.
Wednesday | 2022-04-20 | 14:00 | 19:30 | 5.5 | Design the homepage through figma, if I meet any questions and problems, I will try to find tutorial on Youtube. | Project development | Got the design of homepage, and decided the color and font and layout.
Thursday | 2022-04-21 | 17:00 | 18:00 | 1 | Scrum group meeting, I presented my design and got the advices. | Project management / Scrum meeting | My next action is to adjust some part and design the degree page.
|  | 20:00 | 23:00 | 3 | Adjust the layout and learn the auto-layer concept in Figma and transfer my frames into auto-layer | Project development | Got the first version of the homepage.
Friday | 2022-04-22 | 11:00 | 15:00 | 4 | Design the degree structure page | Project development | Finish the design before the scrum meeting.
|  | 15:00 | 16:00 | 1 | Scrum group meeting, we decided what to show Claudia on client meeting. | Project management / Scrum meeting | I was assigned to establish the template of client meeting minutes. So I will do that later.
|  | 19:00 | 20:30 | 1.5 | Write client meeting minutes in sprint 2 and establish the template of it. | Project management | My next step is to write the homepage in HTML and CSS code.
Saturday | 2022-04-23 | 14:00 | 19:00 | 5 | Have the code of homepage. | Project development | Basically have a static page, cannot interact but it is similar to the design.
Sunday | 2022-04-24 | 21:00 | 22:00 | 1 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. | Self management | Finished the timesheet of this week. This week I mainly did front-end development.
|  |  | Total | 29