## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | 2 (07/03/2022 - 13/03/2022)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-03-07 | 13:00 | 13:15 | 0.25 | Client meeting | project management / Client meeting | In the client meeting, Claudia gave us more specific details towards her needs. She asked us to give her a wireframe first.
|  | 13:15 | 13:45 | 0.5 | Sprint 1 group meeting | Project management / Scrum meeting | Members were allocated the task and separate into front-end team and back-end team.
Tuesday | 2022-03-08 | 18:45 | 20:45 | 2 | Research on what is wireframe and what tool to use | wireframe phase of the development | I decided to use Balsamiq as the tool to draw the wireframe design
Wednesday | 2022-03-09 | 10:00 | 12:30 | 2.5 | Draw draft wireframe of homepage, degree page and course page | wireframe phase of the development | I finished the homepage and degree page and course page wireframe draft sketch.
|  | 14:00 | 15:30 | 1.5 | Sprint 1 group meeting | Project management / Scrum meeting | I got the feedback and advices from my team members for my draft. I will do some adjustment and draw through the Balsamiq tool.
|  | 20:00 | 22:30 | 1 | Learn HTML Introduction session from 'The Complete 2022 Web Development Bootcamp' | Learning basic skill to support my development | I made the notes while studying. Learnt basic structure, lists, image elements, links and anchor tags.
Thursday | 2022-03-10 | 20:00 | 21:30 | 1.5 | Draw homepage wireframe through Balsamiq | wireframe phase of the development | I kept refining the design during drawing.
|  | 23:10 | 2:10 | 3 | Draw degree page and course page wireframe through Balsamiq | wireframe phase of the development | Finished the wireframe design, waiting for the feedback from Claudia
Friday | 2022-03-11 | 0:00 | 15:00 | 3 | Sprint 1 group meeting | Project management / Scrum meeting | This is the first sprint, a lot of rules and principles will be decided during this phase. We generally clarified what we are our goals in each sprint.
|  | 23:00 | 0:00 | 1 | Finish 'test'part of Gantt Chart and other documentations | project management | I finished my part of the Gantt Chart.
Saturday | 2022-03-12 | 20:00 | 22:00 | 2 | Learn HTML Intermediate session from 'The Complete 2022 Web Development Bootcamp' | Learning basic skill to support my development | I learnt about the tables and forms in HTML.
Sunday | 2022-03-13 | 14:00 | 17:00 | 3 | Learn CSS Introduction session from 'The Complete 2022 Web Development Bootcamp' | Learning basic skill to support my development | I learnt aboout inline,internal and external CSS and how to debug CSS code.
|  | 18:30 | 19:00 | 0.5 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. | Self management | Finished the timesheet of this week. And I found my progress in learning new language is a little slow. Next week should put more efforts in it.
|  |  | Total | 21.75