## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | 5 (28/03/2022 - 03/04/22)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-03-28 | 11:00 | 12:15 | 1.25 | Scrum group meeting, in this meeting,we will introduce our own parts and discuss how to revise | Project management / Scrum meeting | We got the feedback from others and need to refine the slides. After that we will send that to Cruz to have the feedback.
|  | 12:15 | 13:00 | 0.75 | Write the meeting minutes, sort out the tasks to do and allocate to other members. | Project management | Next action is to finish my part of the task. Revise the slides.
|  | 17:00 | 21:30 | 4.5 | Refine my part of pitch slide and speech script | Project management / Pitch assignment | I finished my part of pitch slide and speech script
Tuesday | 2022-03-29 | 1:30 | 2:15 | 0.75 | Send the email to Cruz to get the feedback, before sending, refine some details such as font and grammar of the whole slides. | Project management / Pitch assignment | Email sent, waiting for the reply.
|  | 22:00 | 2:00 | 4 | We got the reply from Cruz, we need to refine the slides according to Cruz's feedback. My part needs to have a big adjustment. Meantime, I revised my speech script. | Project management / Pitch assignment | Going to have a rehearsal of my own part tomorrow.
Wednesday | 2022-03-30 | 13:00 | 15:00 | 2 | Rehearse my part of presentation before next scrum meeting | Project management / Pitch assignment | Prepared for the scrum meeting. I practiced to have my fluent presentation.
|  | 15:00 | 17:45 | 2.75 | In this scrum meeting, we did a team rehearsal, and we gave feedback to the new version of our speech (revised after the feedback). Our original plan is to record the video after this rehearsal, but in the real situation, we found there are still more to revise. So we decided to refine more and have another scrum meeting to have the rehearsal again. | Project management / Scrum meeting | According to the suggestions from my teammates, I need to change the main character of the story from students to curriculum leaders. I need to made a need story.
|  | 20:00 | 20:30 | 0.5 | Write the meeting minutes, sort out the tasks to do and allocate to other members. Update the task rotation as we decided to have one week in the midbreak as normal working week. | Project management | After time is time to revise my slides again.
|  | 20:30 | 22:00 | 1.5 | Revise my slides and scripts again. Also rehearsed and counted the time. | Project management / Pitch assignment | Next action is to rehearse again in the scrum meeting.
Thursday | 2022-03-31 | 18:00 | 20:30 | 2.5 | Scrum meeting,we did the rehearsal, I think that's about to be the final version. And we allocated the task towards the business case and draft plan. | Project management / Scrum meeting | In the scrum meeting we gave the advices to each other and decided the last version and everyone can start recording.
|  | 20:30 | 21:15 | 0.75 | Write the meeting minutes, sort out the tasks to do and allocate to other members. | Project management | Next action is to start recording the videos.
Friday | 2022-04-01 | 12:00 | 19:00 | 7 | Start to record the video, I don't know why when I watch my video, I found the video after transcoding is blur and has frame dropping. So I recorded for about 7 times. | Project management / Pitch assignment | Finally I found that it is my player on computer does not support the mp4 format. The video I recorded have no problem at all.
|  | 20:30 | 12:00 | 3.5 | I need to download other teammates' video, and try to combine all videos together. And submit the assignment on behalf of our team. | Project management / Pitch assignment | Everyone had different resolution, it took a while for me to learn how to combine them into a video with size.And upload the video to Youtube and submit the slides.
Satuday | 2022-04-02 | 10:00 | 10:30 | 0.5 | Write an email to Cruz to let her know that we finished and submitted the pitch video and slides. | Project management | Next is to start the bcase and draft plan assignment.
|  | 10:30 | 11:30 | 1 | For the business case and draft plan, me and Yuhao divided the parts. And I checked the marking criteria. | Project management / Bcase & draft plan | I will mainly in charge of why part.
|  | 20:00 | 22:00 | 2 | Writing the business case based on the pitch scripts. | Project management / Bcase & draft plan | Waiting for the feedback from teammates.
Sunday | 2022-04-03 | 19:00 | 22:00 | 3 | Revise my part according to the feedbacks from my teammates. | Project management / Bcase & draft plan | Next step is going to discuss on the scrum meeting.
|  | 22:00 | 23:00 | 1 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. Also recap the week that I become the scrum master for the first time. | Self management | Finished the timesheet of this week. This week is a struggling week, because of the sick leave of last week, this week I have to spend more time on finishing the previous and upcoming assignments. So we can tell from the time sheet that I didn't spend time on developing and learning in this week.
|  |  | Total | 39.25