## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | week 7 (25/04/2022 - 01/05/2022)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-04-25 | 13:00 | 14:30 | 1.5 | Scrum group meeting, we update our progress and allocate the tasks. | Project management / Scrum meeting | I should keep working on page design and coding.
Tuesday | 2022-04-26 | 14:00 | 19:30 | 5.5 | Design another version of degree structure page, the kanban style did not get good feedback from teammates. | Project development | There are differences between degrees in their structure. Some degrees have sub-majors and some degrees have choice streams. So in next step, I need to check the data we got.
|  | 18:00 | 20:30 | 2.5 | Look through all six degree, I need to re-design the hierarchy of the degree. | Project development | Next step is to revise the design the page.
Wednesday | 2022-04-27 | 15:00 | 16:30 | 1.5 | Scrum group meeting, we assigned milestone 1 report for Thursday's workshop. | Project management / Scrum meeting | My part is the reflection of problems.
|  | 18:00 | 19:00 | 1 | Finish my part of milestone report 1. | Project management / Milestone Report 1 | Next step is to revise the design on Figma.
Thursday | 2022-04-28 | 14:00 | 19:00 | 5 | Have the code of degree structure page. | Project development | It is just the code of the layout, haven't connected with the database yet.
Friday | 2022-04-29 | 13:00 | 14:45 | 1.75 | Scrum group meeting, we had a retrospective sprint, we mentioned what went well and what needed improvement. | Project management / Scrum meeting | We realize the speed of page design is slow. I should work more efficiently.
Saturday | 2022-04-30 | 14:00 | 19:00 | 5 | Debug the homepage. It has small problems such as text going out of the card, the drop-down box doesn't work well. | Project development | Figured out the text overflow problem, but still working on interactive stuff on the page.
Sunday | 2022-05-01 | 21:00 | 22:00 | 1 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. | Self management | Finished the timesheet of this week. I should work harder on design pages next week.
|  |  | Total | 24.75