## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-04-25 | 1:00 | 2:30 | 3 | Scrum meeting to reflect last week and make plan for this week | Agile development process | I should clean data we collected and set route for searching functionality
Tuesday | 2022-04-26 | 14:00 | 4:00 | 2 | Clean data: separate course data into three columns: subject title, course code and course name | To make clean data so as to improve the efficiency of accessing data from database | Next I will set route for searching functionality
Wednesday | 2022-04-27 | 10:00 | 12:10 | 5 | set routes for searching functionality | To implement searching functionality | Finished
|  | 3:00 | 4:20 |  | Scrum meeting to reflect on current progress and decide next step | Agile development process | We should do the milestone report
Thursday | 2022-04-28 | 11:00 | 12:00 | 1.3 | Write milestion 1 report | Assignment | Finished
|  | 14:00 | 14:17 |  | Refine technical documentation | To give front end member a clear description | Finished
Friday | 2022-04-08 | 13:00 | 13:38 | 1.5 | Scrum meeting to reflect on current progress and decide next step | Agile development process | After front end finish html/css I will futher integrate them into backend
Sunday | 2022-04-10 | 19:00 | 21:30 | 2.5 | Fix bugs on 2nd version of homepage and turn to ejs file | To fulfill milestone 1 | Finished
|  |  | Total | 15.3