## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID |  | a1818938 |  | Week starting: | 7/3-12/3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-07 | 13:00 | 15:00 | 2 | client and group meeting | Get the detail about our project and decide what to do next | figure out how to develop this project
Tuesday | 2022-03-08 | 14:00 | 19:00 | 5 | lecture and workshop content | decide group meeting time | allocate role in team
Wednesday | 2022-03-09 | 14:00 | 19:00 | 5 | group meeting and scraping soft research | decide role, get raw data | plan to use web scraper, learn how to use it
Thursday | 2022-03-10 | 14:00 | 19:00 | 5 | meeting with a group member decide database structure, try to use web scraper | get raw data from adelaide degree finder | some course structure is different that cause some problem
Friday | 2022-03-11 | 12:00 | 14:00 | 2 | team meeting | decide next steps and team management
Saturday | 2022-03-12 | 19:00 | 23:00 | 4 | modify raw data and learn sql | put raw data into database | transfer csv to mysql, need more learning
|  |  | Total | 23