## Sheet1
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1812504 |  |  | Week starting: | 3
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-03-14 | 9:30 | 11:30 | 2 | Familarise with the project, research any similar problems have been solved | Have a better understanding on how should we design the project | Next, read more web-development architecture
|  | 13:00 | 14:00 | 1 | Attend the project management meeting in the group | Understand the essential tech stacks I need to learn to deliver this project. | Learn HTML, CSS and JavaScript to a level that I can write a basic function
|  | 15:00 | 16:30 | 1.5 | Read wikipedia page of web architecture | Understand the current web architecture and take it as a project inputs of defining our project | Need to have further reading
Tuesday | 2022-03-15 | 9:30 | 11:30 | 2 | Following the Linkedin course Software Design: From Requirements to Release | Have a better understanding on how should we break down oral requirements to actionable development tasks | Finished the 1h58mins course
|  | 14:00 | 16:00 | 2 | Watch this week’s lecture | Have a better understanding on project management | write a lecture notes and share it in the group
Wednesday | 2022-03-16 | 12:00 | 16:00 | 4 | Follow the W3school HTML tutorial | HTML is essential knowledge for me to develop our Web application | Next, try to write a simple personal website only using HTML
Thursday | 2022-03-17 | 10:00 | 12:00 | 2 | Continue the W2scholl HTML tutorial from images to forms | HTML is essential knowledge for me to develop our Web application | Finished the simple text website, next try to learn CSS so this website can have some style
|  | 13:40 | 3:40 | 2 | Discuss the data scope of our project with group member | Understand the project requirements | Next, maybe take further actions to email our client
|  | 17:00 | 18:00 | 1 | Research on what is pitch and what I can do to make our product appealing | Have a better understanding on how will we do our assignments | Wrote a pitch slides structure and the group reviewed on Friday’s meeting
Friday | 2022-03-18 | 11:00 | 13:00 | 2 | Follow the W3school CSS tutorial | To learn essential programming skills | Next, practice on my simple text website to make it looks more nicer.
|  | 13:10 | 14:10 | 1 | Attended group meeting | Communicate with other team members effectively so we know each other’s skillset and progress | Determine the pitch slide structure and divided up the tasks
|  |  | Total | 20.5