## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | Mid-break 1&2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-04-11 | 13:00 | 13:30 | 0.5 | Discuss the database and data structure with Yuhao. And clarify our work division | To make sure the acutal database conforms to the design. Avoid us doing the same thing | I will be responsible for making route for the api that will be used to search the database.
Saturday | 2022-04-16 | 13:00 | 14:30 | 1.5 | Learn Mern Stack, especially to know how to link react UI and node server | To learn essential programming skills | I know how react works and I can use axios to link react UI and node server
Tuesday | 2022-04-19 | 14:00 | 16:30 | 2.5 | group meeting to discuss next sprint and tasks | Project development | I will need to finish some task by the end of this week
|  | 18:30 | 21:30 | 3.75 | Learn how to use git to link to github, clean up the master branch | Project development | I still need to learn how to use git
Wednesday | 2022-04-20 | 11:00 | 11:30 | 0.5 | Make a formal requirement documentation | To give a clear direction to our team | I will next design software architecture
|  | 12:00 | 14:30 | 2.5 | Design our software architecture | To let all the members know what our web application will look like and what services it will support | Finish the design and upload to our Onedrive
Thursday | 2022-04-21 | 17:00 | 18:00 | 1 | Group meeting to discuss the future step in order to achieve milestone 1 | To achieve milestion 1 and improve development efficiency | Members have been assigned different tasks
|  | 18:00 | 20:00 | 2 | Set routes and the functions that will call in these route | To achieve milestion 1 and improve development efficiency | Unfinished, still need more time
|  | 20:00 | 22:00 | 2.5 | Draft the technical document | To let all the members know what our web application will look like and what services it will support | Finished drafting the technical document
Friday | 2022-04-22 | 11:00 | 14:00 | 3 | Set routes and the functions that will call in these route | To achieve milestion 1 and improve development efficiency | Finished, next is to build controllers
Saturday | 2022-04-23 | 11:00 | 2:00 | 4 | Set controllers and refactor the database connection | To achieve milestion 1 and improve development efficiency | Finished. Now our website only need the static html which is the work of front end member
|  | 3:00 | 5:00 | 2 | Document group meeting agenda and minutes in sprint 3 | Project development | Finished
|  |  | Total | 25.75