## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1790940 |  |  | Week starting: | 7
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-04-25 | 1:00 | 2:30 | 3 | Scrum meeting to reflect last week and make plan for this week | Agile development process | I should clean data we collected and set route for searching functionality
Tuesday | 2022-04-26 | 14:00 | 4:00 | 2 | Clean data: separate course data into three columns: subject title, course code and course name | To make clean data so as to improve the efficiency of accessing data from database | Next I will set route for searching functionality
Wednesday | 2022-04-27 | 10:00 | 12:10 | 5 | set routes for searching functionality | To implement searching functionality | Finished
|  | 3:00 | 4:20 |  | Scrum meeting to reflect on current progress and decide next step | Agile development process | We should do the milestone report
Thursday | 2022-04-28 | 11:00 | 12:00 | 1.3 | Write milestion 1 report | Assignment | Finished
|  | 14:00 | 14:17 |  | Refine technical documentation | To give front end member a clear description | Finished
Friday | 2022-04-08 | 13:00 | 13:38 | 1.5 | Scrum meeting to reflect on current progress and decide next step | Agile development process | After front end finish html/css I will futher integrate them into backend
Sunday | 2022-04-10 | 19:00 | 21:30 | 2.5 | Fix bugs on 2nd version of homepage and turn to ejs file | To fulfill milestone 1 | Finished
|  |  | Total | 15.3 | This week I spent less time on MCI project. The reason is that, I, responsible for back end development, has achieved all the required product in back end during midbreak. And it turns out that back end is developed much faster than front end. There are still some works in back end need to wait until front end can finish something. So I expect next week front end members can make some progress so that the back end can continue.