## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID: | a1835541 |  |  | Week starting: | week 8 (02/05/2022-08/05/2022)
Day | Date | Time In | Time Out | Total hours | Task | How does it fit into project plan? | Outcome/Next action
Monday | 2022-05-02 | 13:00 | 13:30 | 0.5 | Client meeting with Claudia | Project management / Client meeting | I will keeping on finishing the course page and search result page design. At the meantime, I will modify the previous design to add the editing function to them.
|  | 13:30 | 15:00 | 1.5 | Group meeting to discuss how to implement Claudia's new request and allocate the task to everyone | Project management / Scrum meeting
|  | 16:00 | 18:00 | 2 | Write the group meeting agenda and minutes of second midbreak week | Project management | Finish first week meeting agenda and minutes of Sprint 4
|  | 21:45 | 23:45 | 2 | Write the Client meeting minutes of today (Sprint 5) | Project management | Finish client meeting agenda of Sprint 5
|  | 23:00 | 1:00 | 2 | Write the group meeting agenda and minutes of week 7. | Project management | Finish second week meeting agenda and minutes of Sprint 4
Tuesday | 2022-05-03 | 14:12 | 16:27 | 2.25 | Design draft UI of Homepage - Course section | Project development | Already written design instruction and post on group chat, waiting for the feedback from team members.
|  | 16:20 | 17:35 | 1.25 | Design draft UI of search result page | Project development | Already written design instruction and post on group chat, waiting for the feedback from team members.
Wednesday | 2022-05-04 | 13:00 | 15:00 | 2 | Group meeting to display my draft design and get feedback from teammates | Project management / Scrum meeting | Got the feedback from teammates and can start to code
|  | 21:10 | 21:40 | 0.5 | Send Claudia an email and ask for choice of the design,and ask questions that we are not sure about. | Project development | Waiting for the feedback from Claudia and do the change from her reply.
Thursday | 2022-05-05 | 16:00 | 19:00 | 3 | Revise the course card design according to the feedback of Claudia. | Project development | Deleted the design of assumed knowledge and refined the course card design that Claudia chose.
Friday | 2022-05-06 | 11:30 | 15:00 | 3.5 | Revise the detail part of the homepage, change the degree card style. | Project development | Already have the basic structure of the HTML page, the later work is to make the drop-down button and switch button can interact.
|  | 3:00 | 4:30 | 1.5 | Group meeting to display my new version design and show the basic structure with code. | Project management / Scrum meeting | The Homepage design is basically decided,just need to adjust some details and interactions in code. Also members gave advices on how to revise my part of Milestone 1 report. I will do it later.
|  | 19:15 | 20:15 | 1 | Revise my part in Milestone 1 report. | Project management | I changed the problem part into two main problems, one is sick leave delay the development progress, the other one is the tool that we used for communicating and managing.
Saturday | 2022-05-07 | 12:00 | 17:00 | 5 | Revise the code for the change I made in design. | Project development | During the coding, I also found some tutorial online to teach me how to implement the function I want. Now I have the drop-down button, just need to adjust the detail.
|  | 20:00 | 23:00 | 3 | Revise the degree structure page for it has majors showing below. | Project development | Next step is to have the course detailed page.
Sunday | 2022-05-08 | 21:00 | 22:00 | 1 | Sort out this week's timesheet, and recap what I have done this week and what I should do next week. | Self management | Finished the timesheet of this week. Next week is to finish all page design and have the static code.
|  |  | Total | 31