## Sheet2
MCI Project Weekly Time Sheet
Team | 7 | Student ID | a1812504 |  |  | Week starting: | 2
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2022-03-07 | 8:30 | 8:15 | 0.5 | Send a email reminder to our client and other team member in case anyone miss our meeting in the afternoon | The client’s meeting time slot was discussed in last week, it’s also good habit to send an email reminder to group members on important meetings. | Everyone was punctual on this meeting
Tuesday | 2022-03-08 | 13:00 | 1:30 | 0.5 | Host our first client’s meeting | This is project kick off meeting, we would like to know to ask the very important questions related to our project, especially, 1. what is it? Who is our target audience? Why it is needed? | The client answered our question, and asked us to draw a wireframe to her.
|  | 13:30 | 15:30 | 2 | Host our first formal group meeting | Internal communication | The definition of the most important aspects of our project still need to be further discuss
|  | 17:00 | 18:00 | 1 | Produce the meeting minutes of the kick off meeting and first group meeting | Consistent documentation | Draw our Web Application’s wireframe
Wednesday | 2022-03-09 | 9:30 | 13:30 | 4 | Learn Figma to implement my wireframe design which can fit all device size | Instead of describing in words which could be abstract to our client, it's better to use wireframe to give her an idea | Finished the main page, will continue to work on the degree page and course page tomorrow
|  | 13:30 | 14:00 | 0.5 | Prepare the upcoming group meeting | To have a highly effected meeting | Next, try to have our project initiation document and identify our project members as soon as possible
|  | 14:00 | 16:00 | 2 | hosted the second group meeting | Establish the important project definition and timeline in the first week | In this meeting, we determined these outcome:1. Development role 2. Scrum master rotation 3. Internal communication order
|  | 17:00 | 17:30 | 0.5 | Produce the meeting minutes of this meeting | Consistent documentation | Next, try to draw a wireframe that contains the basic feature design based on our understanding
Thursday | 2022-03-10 | 12:30 | 17:30 | 5 | Finished the design of another two pages | We try to hand in the design as soon as possbile then we can get the feedbacks from our client as soon as possible | Finished my final version of the wireframe design
Friday | 2022-03-11 | 11:30 | 12:00 | 0.5 | Prepare the Sprint 1 Task Update & Retrospective Meeting | Establish the important project definition and timeline in the first week | We alloacted tasks for the Gantt chart in the group and internal organization
|  | 12:00 | 3:00 | 3 | Host the Sprint 1 Task Update & Retrospective Meeting | To discuss the issues listed above | 1.Allocate Gantt chart editing task 2.Discussed the follow up questions needed to confirm from the client 3. Determined the priorities of the next sprint
|  | 15:00 | 15:30 | 0.5 | Produce the meeting minutes and establish the group documentation | Provide a single and clear documentation source | Next, email the client to clearify the data scope
|  | 15:30 | 17:00 | 1.5 | Sending a formal email to the client to clarify the data scope of our project | Figure out what data we are working on | The client clarified the data scope on Monday
Saturday | 2022-03-12
Sunday | 2022-03-13
|  |  | Total | 21.5